## Implementer Rate Schedule
Implementer Schedule of Rates per hour (discounted where full utilization is expected)
All rates are EXCLUDING VAT | Rate to be used for bidding in the Bill of Services | Name/s of person/s nominated to play this role | Rate for Travelling outside of Gauteng
Management
Implementation Director
Project Manager
Laboratory Manager
Implementation
Strategic Solution Architect
Senior Implementer
Implementer
Junior Implementer
Development
Senior Solution Architect
Senior Developer
Developer
Specialists
Documentation Specialist
Computer Based Training Developer
Typing Instructor
Other Team Members
Other 1
Other 2
Other 3
Other 4
Other 5
Other 6
Other n
Vehicle Rate per km outside of Gauteng
Management
Staff

## Summary of Bill of Services
Client Business System and ERP Procurement
Summary of Bill of Services
| Serial | [5 empty] | Item |  |  |  |  | Questions | Comments |  |  |  |  | Disbursements |  |  | Implementer Team Hours per Category per Activity | [10 empty] | Implementer Team Rands per Category per Activity
[14 empty] | Expected Elapsed Time Weeks |  | Software Cost | Hardware Cost | Travel | Accommodation | Disbursements | Management Team | Total Management Team Hours | Implementation Team | Total Implementation Team Hours | Development Team | Total Development Team Hours | Specialist Team | Total Specialist Team Hours | Other Team Members | Total Other Team Member Hours | Grand Total Hours | Management Team | Total Management Team Rands | Implementation Team | Total Implementation Team Rands | Development Team | Total Development Team Rands | Specialist Team | Total Specialist Team Rands | Other Team Members | Total Other Team Member Rands | Grand Total Rands
[11 empty] | Rates -- Rand per Hour from next sheet |  |  | Low Est | High Est
| 1 | [5 empty] | Finalization of bid -- detailed planning, contracting, etc -- phase 3 of bidding process for selected vendor
| 2 | [5 empty] | Establishment
| 3 | [5 empty] | Project Management and Change Facilitation
|  | 1 | [5 empty] | Project Management and liaison
|  | 2 | [5 empty] | Communication and Change Facilitation
Total Project Management and Change Facilitation
| 4 | [5 empty] | Configuration and Integration of Data Warehouse and Business Intelligence
|  | 1 | [5 empty] | Develop overall solution definition
|  | 2 | [5 empty] | Comprehensive walkthrough of as-delivered tables, ETL, models, dashboards, reports, etc in Data Whouse & BI solution
|  | 3 | [5 empty] | Develop DW & BI for modules not covered in core datawarehouse
Total Data Warehouse and Business Intelligence
| 5 | [5 empty] | Client Business Management Related Software
|  | 1 | [5 empty] | Overall Client Business Management Solution
|  | 2 | [5 empty] | Manage Client Asset Utilization and Turnaround
|  | 3 | [5 empty] | Operations Board
|  | 4 | [5 empty] | Interface with Client Asset Tracking Systems
|  | 5 | [5 empty] | Client Asset Milestone Monitoring and Reporting
|  | 6 | [5 empty] | Load Broking to Sub-Contractors
Total Client Business Specific Modules
| 6 | [5 empty] | Other Specialist Modules
|  | 1 | [5 empty] | Software to Manage Client Asset Operating Costs -- interfacing with third party systems
|  | 2 | [5 empty] | Control and Logging Software -- if development is proposed itemize what is required
|  | 3 | [5 empty] | Software to manage Warehouse Operations
|  | 4 | [5 empty] | Software to Manage Sub-Contractors
|  | 5 | [5 empty] | Software to Manage Quoting
|  | 6 | [5 empty] | CRM -- Internal Instance of Microsoft Dynamics CRM
|  | 7 | [5 empty] | Software for Business Operations -- indicative costs only
Total Specialist Modules
| 7 | [5 empty] | Configuration and Integration of Finance and Administration Modules
398 |  |  | 1 | [5 empty] | General Ledger
|  |  | 2 | [5 empty] | Accounts Receivable
|  |  | 3 | [5 empty] | Accounts Payable
|  |  | 4 | [5 empty] | Cashbook
|  |  | 5 | [5 empty] | Assets Register
|  |  | 6 | [5 empty] | Other Finance
Total Finance
|  | 2 | [5 empty] | Human Resources
|  | 3 | [5 empty] | Payroll
Total Human Resources and Payroll
Total Finance and Administration
| 8 | [5 empty] | Integrated Laboratory testing and laboratory simulation operation
|  | 1 | [5 empty] | Establishment of Laboratory
|  | 2 | [5 empty] | Testing of individual modules
|  | 3 | [5 empty] | Test Integration
|  |  | 1 | [5 empty] | Test integration of modules as they become available
|  |  | 2 | [5 empty] | Testing and acceptance of the integrated solution
|  |  |  | 1 | [5 empty] | Technical integration
|  |  |  | 2 | [5 empty] | Business operational integration
|  |  |  | 3 | [5 empty] | Simulation and review of integrated solution -- first iteration
|  |  |  | 4 | [5 empty] | Simulation and review of integrated solution -- second iteration
|  |  |  | 5 | [5 empty] | Simulation and review of integrated solution -- third iteration
Total Testing of Integrated Solution
|  | 4 | [5 empty] | Development and testing of integrated reports and BI models, etc
|  | 5 | [5 empty] | Specification, configuration, testing, refinement and documentation of integrated workflows / operating procedures -- 3 iterations
|  | 6 | [5 empty] | Development of training materials
|  | 7 | [5 empty] | Training
|  |  | 1 | [5 empty] | Training of Operational Personnel
|  |  | 2 | [5 empty] | Training of Supervisory Personnel
|  |  | 3 | [5 empty] | Training of Managers
Total Training
|  | 8 | [5 empty] | Formal declaration of readiness to commence live operation -- issue certificate of readiness
Total Integrated Laboratory testing and laboratory simulation operation
| 9 | [5 empty] | Custom Development -- lump sum budget provision
| 10 | [5 empty] | Overall System Integration
| 11 | [5 empty] | General System Requirements
| 12 | [5 empty] | Operational commissioning and ramp-up to formal handover including fine tuning and bedding down
|  | 1 | [5 empty] | Develop detailed commissioning plan at the level of each business unit and each functional area -- exec review -- 3 itns
|  | 2 | [5 empty] | Commissioning in xxx2
|  | 3 | [5 empty] | Commissioning in xxx1
|  | 4 | [5 empty] | Commissioning at xxx3 -- very limited scope
|  | 5 | [5 empty] | Formal declaration of project completion and final handover to Client
Total Operational Commissioning, Ramp-Up and Handover
| 13 | [5 empty] | Operational support per 12 month period from anniversary of handover
| 14 | [5 empty] | Contingency
|  | 1 | [5 empty] | Implementer discretion contingency if required by bidder
|  | 2 | [5 empty] | Client discretion contingency only released with Client approval
Grand Totals
Cross Cast -- Error Check
I the undersigned …………………………………….. (name) hereby certify that this schedule has been rigorously quality controlled and represents the definitive pricing for Professional Services for the Client Business System and ERP Project and confirm that …………………………………… (name of company)
will deliver the required solution for the prices shown here on a fixed price per component basis with a tolerance of 10%, that is that the final offer price will not be more than 10% greater than the price above -- for Stage 1 of the bid process

## Bill of Services
Client Business System and ERP Procurement
Bill of Services
NOTES to bidders
There are three tabs in this spreadsheet -- Rates, Summary and Detail -- all three must be completed and printed
The item numbering in this spreadsheet, as ammended during detailed planning is required to form the backbone of the Gantt chart
This schedule is detailed in order to ensure that all costs are accurately catered for, Bidders are free to quote in less detail if they choose to
Bidders are free to insert lines as required to accurately reflect their approach -- ONLY FULL LINES MAY BE INSERTED
Where an additional software module or other plan component is added please copy and existing block and adhere to the conventions used here
Bidders are free to IGNORE and leave BLANK any item that they consider to be not applicable or not material LINES MAY NOT BE DELETED
Note that executive review may involve one executive for a few minutes reviewing a document or running through a prototype
-- it does NOT need to be a lengthy process
Bidders can add additional categories of personnel to the rates table -- they may NOT rename or add categories
Categories must be added BEFORE "Other n" and corresponding columns added to the table
There are no formulae in the spreadsheet, bidders must add their own formulae and are accountable for the accuracy of their formulae
-- totals and sub-totals must be supplied in the rows and columns provided
Client will NOT pay for travelling time or kilometers within Gauteng, will only pay for travel and accomodation outside of Gauteng
There will be NO additional disbursements, travel time or travel costs permitted over and above what is in this schedule unless claimed against the
the capped contingency provided for below
Note that just because a line or column is present does NOT mean that bidders are required to put a number against those items
this document constitutes a framework so that all bidders offers can be compared effectively
| Serial | [5 empty] | Item | [5 empty] | Questions | Comments |  |  |  |  | Disbursements |  |  | Implementer Team Hours per Category per Activity | [31 empty] | Implementer Team Rands per Category per Activity
[15 empty] | Expected Elapsed Time Weeks |  | Software Cost | Hardware Cost | Travel | Accommodation | Disbursements | Management Team | Implementation Director | Project Manager | Laboratory Manager | Total Management Team Hours | Implementation Team | Strategic Solution Architect | Senior Implementer | Implementer | Junior Implementer | Total Implementation Team Hours | Development Team | Senior Solution Architect | Senior Developer | Developer | Total Development Team Hours | Specialist Team | Documentation Specialist | Computer Based Training Developer | Typing Instructor | Total Specialist Team Hours | Other Team Members | Other 1 | Other 2 | Other 3 | Other 4 | Other 5 | Other 6 | Insert here | Other n | Total Other Team Member Hours | Grand Total Hours | Management Team | Implementation Director | Project Manager | Laboratory Manager | Total Management Team Rands | Implementation Team | Strategic Solution Architect | Senior Implementer | Implementer | Junior Implementer | Total Implementation Team Rands | Development Team | Senior Solution Architect | Senior Developer | Developer | Total Development Team Rands | Specialist Team | Documentation Specialist | Computer Based Training Developer | Typing Instructor | Total Specialist Team Rands | Other Team Members | Other 1 | Other 2 | Other 3 | Other 4 | Other 5 | Other 6 | Insert here | Other n | Total Other Team Member Rands | Grand Total Rands
[12 empty] | Rates -- Rand per Hour from next sheet |  |  | Low Est | High Est
1
2 | 1 | [5 empty] | Finalization of bid -- detailed planning, contracting, etc -- phase 3 of bidding process for selected vendor
3 |  | 1 | [5 empty] | Introduction of core team that will run the project -- both sides
4 |  | 2 | [5 empty] | Discovery as required
5 |  | 3 | [5 empty] | Final Definition of Scope in terms of exact modules and products to be procured and implemented
6 |  | 4 | [5 empty] | Develop comprehensive project plan
7 |  | 5 | [5 empty] | Contractual negotiations
8 |  | 6 | [5 empty] | Acceptance and signing of contract
9 |  | 7 | [5 empty] | Other bid finalization activities
10
11
12 | [6 empty] | Total finalization of bid
13
14
15 | 2 | [5 empty] | Establishment
16 |  | 1 | [5 empty] | Introduce full project teams
17 |  | 2 | [5 empty] | Move into project office, connect to network and other settling in
18 |  | 3 | [5 empty] | Agree communication, document management and other protocols
19 |  | 4 | [5 empty] | Install and commission Computer Based Training software
20 | [8 empty] | -- team must included an experienced CBT developer with experience in developing educational material
21 |  | 5 | [5 empty] | Other establishment activities
22
23
24 | [6 empty] | Total establishment
25
26
27 | 3 | [5 empty] | Project Management and Change Facilitation
28 |  | 1 | [5 empty] | Project Management and liaison
29 |  |  | 1 | [5 empty] | Develop detailed project schedule down to +/- 2 week per work package
30 | [9 empty] | -- at monthly Project Status meetings a work package is either not started, in progress or complete
31 | [9 empty] | -- the same package is NOT permitted to be in progress for more than one meeting -- red flag to be raised if break this rule
32 |  |  | 2 | [5 empty] | Quarterly Project Status Review meetings
33 |  |  | 3 | [5 empty] | Monthly Project Board meetings
34 |  |  | 4 | [5 empty] | Monthly Project Status meetings
35 |  |  | 5 | [5 empty] | Weekly Project meetings
36 |  |  | 6 | [5 empty] | Implementer Project Manager in role
37 |  |  | 7 | [5 empty] | Other project management activities
38
39
40 | [7 empty] | Total project management and liaison
41
42 |  | 2 | [5 empty] | Communication and Change Facilitation
43 |  |  | 1 | [5 empty] | Liaison and communication
44 |  |  | 2 | [5 empty] | Develop change facilitation plan
45 |  |  | 3 | [5 empty] | Communication activites
46 |  |  | 4 | [5 empty] | Engagement activies
47 |  |  | 5 | [5 empty] | Problem diagnosis activites
48 |  |  | 6 | [5 empty] | Other change facilitation activities
49
50
51 | [7 empty] | Total Communication and Change Facilitation
52
53 | [6 empty] | Total Project Management and Change Facilitation
54
55
56 | 4 | [5 empty] | Configuration and Integration of Data Warehouse and Business Intelligence
57 |  | 1 | [5 empty] | Develop overall solution definition
58 |  |  | 1 | [5 empty] | Executive workshops -- "if we could give you any information you can think of what would you ask for?"
59 |  |  | 2 | [5 empty] | Operational workshops -- "if we could give you any information you can think of what would you ask for?"
60 |  |  | 3 | [5 empty] | High level conceptual design and review of practicallity and cost implications
61 |  |  | 4 | [5 empty] | Agree portion of budget to be reserved for unexpected requirements once system is operational
62 |  |  | 5 | [5 empty] | Detailed planning of end user Business Intelligence deliverable
63 |  |  | 6 | [5 empty] | Detailed design of end user Business Intelligence deliverable
64 |  |  | 7 | [5 empty] | Agree final scope of Data Warehouse and Business Intelligence solution
65 |  |  | 8 | [5 empty] | Other Data Warehouse and Business Intelligence Solution definition activities
66
67
68 | [7 empty] | Total Develop overall Data Warehouse and Business Intelligence solution definition
69
70 |  | 2 | [5 empty] | Comprehensive walkthrough of as-delivered tables, ETL, models, dashboards, reports, etc in Data Whouse & BI solution
71 |  |  | 1 | [5 empty] | High level analysis of requirements to achieve a total solution
72 |  |  | 2 | [5 empty] | Detailed planning of overall data warehouse configuration and implementation -- including budget related trade-off's
73 |  |  | 3 | [5 empty] | Other Data Warehouse configuration planning activities
74
75
76 | [7 empty] | Total Comprehensive walkthrough of as-delivered DW and BI
77
78 |  | 3 | [5 empty] | Develop DW & BI for modules not covered in core datawarehouse
79 |  |  | 1 | [5 empty] | Familiarization with system and database design
80 |  |  | 2 | [5 empty] | Design schema's
81 |  |  | 3 | [5 empty] | Build database
82 |  |  | 4 | [5 empty] | Specify ETL
83 |  |  | 5 | [5 empty] | Develop ETL
84 |  |  | 6 | [5 empty] | Develop basic inquiry and analysis capability
85 |  |  |  | 1 | [5 empty] | Specify basic models, reports and dashboards
86 |  |  |  | 2 | [5 empty] | Develop basic models, reports and dashboards
87 |  |  | 7 | [5 empty] | Develop intermediate level inquiry and analysis capability
88 |  |  |  | 1 | [5 empty] | Specify intermediate complexity models, reports and dashboards
89 |  |  |  | 2 | [5 empty] | Develop intermediate complexity models, reports and dashboards
90 |  |  | 8 | [5 empty] | Develop advanced level inquiry and analysis capability
91 |  |  |  | 1 | [5 empty] | Specify complex models, reports and dashboards
92 |  |  |  | 2 | [5 empty] | Develop complex models, reports and dashboards
93 |  |  | 9 | [5 empty] | Executive adoption
94 |  |  | 10 | [5 empty] | Other activities relative to the third party module
95
96
97 | [7 empty] | Total warehouse and BI for additional modules
98
99 | [6 empty] | Total Data Warehouse and Business Intelligence
100
101
102 | 5 | [5 empty] | Business Management Related Software
103 |  | 1 | [5 empty] | Overall Business Management Solution
104 |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
105 |  |  | 2 | [5 empty] | Comprehensive walkthroughs of the module
106 |  |  | 3 | [5 empty] | In-depth consultation with Client Business Specialists
107 |  |  | 4 | [5 empty] | Develop best practice standards for configuration in Client
108 |  |  | 5 | [5 empty] | Develop Client codes facilitated by JAR
109 |  |  | 6 | [5 empty] | Laboratory configuration and testing
110 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
111 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
112 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
113 |  |  |  | 4 | [5 empty] | Specify, document and test module specific workflows (processes)
114 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
115 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution
116 |  |  | 7 | [5 empty] | Adoption of solution
117 |  |  | 8 | [5 empty] | Other Business Management module configuration and integration related activities
118
119
120 | [8 empty] | Total Overall Business Management Solution
121
122 |  | 2 | [5 empty] | Manage Client Asset Utilization
123 |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
124 |  |  | 2 | [5 empty] | Comprehensive walkthroughs of the module
125 |  |  | 3 | [5 empty] | In-depth consultation with Client Specialists
126 |  |  | 4 | [5 empty] | Develop best practice standards for configuration in Client
127 |  |  | 5 | [5 empty] | Develop Client codes facilitated by JAR
128 |  |  | 6 | [5 empty] | Laboratory configuration and testing
129 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
130 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
131 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
132 |  |  |  | 4 | [5 empty] | Specify, document and test module specific workflows (processes)
133 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
134 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution with executives
135 |  |  | 7 | [5 empty] | Adoption of solution
136 |  |  | 8 | [5 empty] | Other Client Asset Utilization and Turnaround module configuration and integration related activities
137
138
139 | [7 empty] | Total Client Asset Utilization and Turnaround
140
159
160 |  | 4 | [5 empty] | Interface with Client Asset Tracking Systems
176
177 | [7 empty] | Total Interface with Client Asset Tracking Systems
178
179 |  | 5 | [5 empty] | Client Asset Milestone Monitoring and Reporting
195
196 | [7 empty] | Total Client Asset Milestone Monitoring and Reporting
197
218
219
220 | 6 | [5 empty] | Other Specialist Modules
221 |  | 1 | [5 empty] | Software to Manage Client Asset Operating Costs -- interfacing with third party systems
222 |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
223 |  |  | 2 | [5 empty] | Integration must be comprehensively proven with site references if a 3rd party product is proposed
224 |  |  | 3 | [5 empty] | Design integration with third party systems if not already proven
225 |  |  | 4 | [5 empty] | Comprehensive walkthroughs of the module
226 |  |  | 5 | [5 empty] | In-depth consultation with Client subject matter experts
227 |  |  | 6 | [5 empty] | Develop best practice standards for configuration in Client
228 |  |  | 7 | [5 empty] | Develop Client codes guided by JAR
229 |  |  | 8 | [5 empty] | Laboratory configuration and testing
230 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
231 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
232 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
233 |  |  |  | 4 | [5 empty] | Specify, document and test workflows (processes)
234 |  |  |  | 5 | [5 empty] | Specify & develop Computer Based Training material
235 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution
236 |  |  | 9 | [5 empty] | Other Client Asset Operating Cost module configuration and integration related activities
237
238
239 | [7 empty] | Total Software to Manage Client Asset Operating Costs
240
241 |  | 2 | [5 empty] | Check Bay Control and Logging Software -- if development is proposed itemize what is required
242 |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
243 |  |  | 2 | [5 empty] | Integration must be comprehensively proven with site references if a 3rd party product is proposed
244 |  |  | 3 | [5 empty] | Comprehensive walkthroughs of the module
245 |  |  | 4 | [5 empty] | In-depth consultation with Client subject matter experts
246 |  |  | 5 | [5 empty] | Develop best practice standards for configuration
247 |  |  | 6 | [5 empty] | Develop Client codes facilitated by JAR
248 |  |  | 7 | [5 empty] | Coordinate with other modules
249 |  |  | 8 | [5 empty] | Laboratory configuration and testing
250 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
251 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
252 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
253 |  |  |  | 4 | [5 empty] | Specify, document and test module specific workflows (processes)
254 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
255 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution with executives
256 |  |  | 9 | [5 empty] | Other Check Bay Control and Logging module configuration and integration activities
257
258
259 | [7 empty] | Total Materials Management and Tracking
260
261 |  | 3 | [5 empty] | Software to manage Consolidation Center Operations
262 |  |  | 1 | [5 empty] | Liaison and consultation with package specialists
263 |  |  | 2 | [5 empty] | Integration must be comprehensively proven with site references if a 3rd party product is proposed
264 |  |  | 3 | [5 empty] | Comprehensive walkthroughs of the module
265 |  |  | 4 | [5 empty] | In-depth consultation with Client subject matter experts
266 |  |  | 5 | [5 empty] | Develop best practice standards for configuration
267 |  |  | 6 | [5 empty] | Develop Client module specific codes facilitated by JAR
268 |  |  | 7 | [5 empty] | Coordinate with other modules
269 |  |  | 8 | [5 empty] | Laboratory configuration and testing
270 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
271 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
272 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
273 |  |  |  | 4 | [5 empty] | Specify, document and test module processes
274 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
275 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution
276 |  |  | 9 | [5 empty] | Other Consolidation Center configuration and integration related activities
277
278
279 | [7 empty] | Total Consolidation Center
280
281 |  | 4 | [5 empty] | Software to Manage Sub-Contractors
300
301 |  | 5 | [5 empty] | Software to Manage Quoting
319
320 |  | 6 | [5 empty] | CRM -- Internal Instance of Microsoft Dynamics CRM
321 |  |  | 1 | [5 empty] | Liaison and consultation with module specialists at …
322 |  |  | 2 | [5 empty] | Compliance with Group standards
323 |  |  | 3 | [5 empty] | Comprehensive walkthroughs of the module
324 |  |  | 4 | [5 empty] | In-depth consultation with Client subject matter experts
325 |  |  | 5 | [5 empty] | Develop best practice standards for configuration
326 |  |  | 6 | [5 empty] | Develop Client module specific codes facilitated by JAR
327 |  |  | 7 | [5 empty] | Laboratory configuration and testing
328 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
329 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
330 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
331 |  |  |  | 4 | [5 empty] | Specify, document and test module processes
332 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
333 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution
334 |  |  | 7 | [5 empty] | Other CRM configuration and integration related activities
335
336
337 | [7 empty] | Total CRM -- Microsoft Dynamics CRM
338
376
377 |  | 9 | [5 empty] | Proof of Delivery Documentation Management
392
393
394 | [7 empty] | Total Proof of Delivery Document Management
395
396 | [6 empty] | Total Specialist Modules
397
398
399 | 7 | [5 empty] | Configuration and Integration of Finance and Administration Modules
400 |  | 1 | [5 empty] | Finance
401 |  |  | 1 | [5 empty] | General Ledger
402 |  |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
403 |  |  |  | 2 | [5 empty] | Comprehensive walkthroughs of the module
404 |  |  |  | 3 | [5 empty] | In-depth consultation with Client subject matter experts
405 |  |  |  | 4 | [5 empty] | Develop best practice standards for configuration
406 |  |  |  | 5 | [5 empty] | Develop Client Chart of Accounts to JAR&A standards
407 |  |  |  | 6 | [5 empty] | Laboratory configuration and testing
408 |  |  |  |  | 1 | [5 empty] | General ledger integration must be tested with ALL modules with financial elements
409 |  |  |  |  | 2 | [5 empty] | Develop workflows, standards, policies and protocols
410 |  |  |  |  | 3 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
411 |  |  |  |  | 4 | [5 empty] | Configure in the Laboratory, test and refine
412 |  |  |  |  | 5 | [5 empty] | Specify, document and test module processes
413 |  |  |  |  | 6 | [5 empty] | Specify and develop module specific Computer Based Training material
414 |  |  |  |  | 7 | [5 empty] | Final presentation and walkthrough of entire solution
415 |  |  |  | 7 | [5 empty] | Other General Ledger module configuration and integration related activities
416
417
418 | [8 empty] | Total General Ledger
419
420 |  |  | 2 | [5 empty] | Accounts Receivable
421 |  |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
422 |  |  |  | 2 | [5 empty] | Comprehensive walkthroughs of the module
423 |  |  |  | 3 | [5 empty] | In-depth consultation with Client subject matter experts
424 |  |  |  | 4 | [5 empty] | Develop best practice standards for configuration
425 |  |  |  | 5 | [5 empty] | Develop Client codes facilitated by JAR
426 |  |  |  | 6 | [5 empty] | Laboratory configuration and testing
427 |  |  |  |  | 1 | [5 empty] | Invoicing must integrate tightly with Financials
428 |  |  |  |  | 2 | [5 empty] | Develop workflows, standards, policies and protocols
429 |  |  |  |  | 3 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
430 |  |  |  |  | 4 | [5 empty] | Configure in the Laboratory, test and refine
431 |  |  |  |  | 5 | [5 empty] | Specify, document and test module processes
432 |  |  |  |  | 6 | [5 empty] | Specify and develop module specific Computer Based Training material
433 |  |  |  |  | 7 | [5 empty] | Final presentation and walkthrough of entire solution
434 |  |  |  | 7 | [5 empty] | Other Accounts Receivable module configuration and integration related activities
435
436
437 | [8 empty] | Total Accounts Receivable
438
439 |  |  | 3 | [5 empty] | Accounts Payable
440 |  |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
441 |  |  |  | 2 | [5 empty] | Comprehensive walkthroughs of the module
442 |  |  |  | 3 | [5 empty] | In-depth consultation with Client subject matter experts
443 |  |  |  | 4 | [5 empty] | Develop best practice standards for configuration
444 |  |  |  | 5 | [5 empty] | Develop Client codes facilitated by JAR
445 |  |  |  | 6 | [5 empty] | Laboratory configuration and testing
446 |  |  |  |  | 1 | [5 empty] | Accounts payable must integrate tightly with invoicing with regard to payment of sub-contractors
447 |  |  |  |  | 2 | [5 empty] | Develop workflows, standards, policies and protocols
448 |  |  |  |  | 3 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
449 |  |  |  |  | 4 | [5 empty] | Configure in the Laboratory, test and refine
450 |  |  |  |  | 5 | [5 empty] | Specify, document and test module processes
451 |  |  |  |  | 6 | [5 empty] | Specify and develop module specific Computer Based Training material
452 |  |  |  |  | 7 | [5 empty] | Final presentation and walkthrough of entire solution
453 |  |  |  | 7 | [5 empty] | Other Accounts Payable module configuration and integration related activities
454
455
456 | [8 empty] | Total Accounts Payable
457
458 |  |  | 4 | [5 empty] | Cashbook
459 |  |  |  | 1 | [5 empty] | Comprehensive walkthroughs of the module
460 |  |  |  | 2 | [5 empty] | Develop Client codes facilitated by JAR
461 |  |  |  | 3 | [5 empty] | Laboratory configuration and testing
462 |  |  |  |  | 1 | [5 empty] | Identify any Client specific Cashbook requirements
463 |  |  |  |  | 2 | [5 empty] | Develop workflows, standards, policies and protocols
464 |  |  |  |  | 3 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
465 |  |  |  |  | 4 | [5 empty] | Configure in the Laboratory, test and refine
466 |  |  |  |  | 5 | [5 empty] | Specify, document and test module processes
467 |  |  |  |  | 6 | [5 empty] | Specify and develop module specific Computer Based Training material
468 |  |  |  |  | 7 | [5 empty] | Final presentation and walkthrough of entire solution
469 |  |  |  | 4 | [5 empty] | Other Cashbook related configuration and integration activities
470
471
472 | [8 empty] | Total Cashbook
473
474 |  |  | 5 | [5 empty] | Assets Register
475 |  |  |  | 1 | [5 empty] | Liaison and consultation with module specialists
476 |  |  |  | 2 | [5 empty] | Comprehensive walkthroughs of the module
477 |  |  |  | 3 | [5 empty] | In-depth consultation with Client subject matter experts
478 |  |  |  | 4 | [5 empty] | Develop best practice standards for configuration
479 |  |  |  | 5 | [5 empty] | Develop Client codes facilitated by JAR
480 |  |  |  | 6 | [5 empty] | Coordinate with Fleet Management and Business Management Modules
481 |  |  |  | 7 | [5 empty] | Laboratory configuration and testing
482 |  |  |  |  | 1 | [5 empty] | Assets Register must integrate tightly with Fleet Maintenance module and other related modules
483 |  |  |  |  | 2 | [5 empty] | Develop workflows, standards, policies and protocols
484 |  |  |  |  | 3 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
485 |  |  |  |  | 4 | [5 empty] | Configure in the Laboratory, test and refine
486 |  |  |  |  | 5 | [5 empty] | Specify, document and test module processes
487 |  |  |  |  | 6 | [5 empty] | Specify and develop module specific Computer Based Training material
488 |  |  |  |  | 7 | [5 empty] | Final presentation and walkthrough of entire solution
489 |  |  |  | 8 | [5 empty] | Other Asset Register module related configuration and integration activities
490
491
492 | [8 empty] | Total Assets Register
493
494 |  |  | 6 | [5 empty] | Other Finance
495 |  |  |  | 1 | [5 empty] | Activities as necessary to fully configure and commission other module/s -- list in same detail as above
496
497
498 | [8 empty] | Total Other Finance
499
500 | [7 empty] | Total Finance
501
502 |  | 2 | [5 empty] | Human Resources
503 |  |  | 1 | [5 empty] | Must integrate with other modules which tie in to personnel data
504 |  |  | 2 | [5 empty] | In-depth evaluation of proposed solution relative to existing product
505 |  |  | 3 | [5 empty] | Liaison and consultation with package specialists
506 |  |  | 4 | [5 empty] | Integration must be comprehensively proven with site references
507 |  |  | 5 | [5 empty] | Comprehensive walkthroughs of the module
508 |  |  | 6 | [5 empty] | In-depth consultation with Client subject matter experts
509 |  |  | 7 | [5 empty] | Develop best practice standards for configuration
510 |  |  | 8 | [5 empty] | Develop Client module specific codes facilitated by JAR
511 |  |  |  | 1 | [5 empty] | Develop knowledge and experience (competence / skills) categorization
512 |  |  |  | 2 | [5 empty] | Develop other HR module specific codes
513 |  |  | 9 | [5 empty] | Coordinated with Business and other modules
514 |  |  | 10 | [5 empty] | Laboratory configuration and testing
515 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
516 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
517 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
518 |  |  |  | 4 | [5 empty] | Specify, document and test module processes
519 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
520 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution
521 |  |  | 11 | [5 empty] | Other Human Resource module configuration and integration related activities
522
523
524 | [7 empty] | Total Human Resources
525
526 |  | 3 | [5 empty] | Payroll
527 |  |  | 1 | [5 empty] | Must integrate with Business and other modules which tie in to personnel data and cost data
528 |  |  | 2 | [5 empty] | In-depth evaluation of proposed solution relative to existing product --
529 |  |  | 3 | [5 empty] | Liaison and consultation with package specialists
530 |  |  | 4 | [5 empty] | Integration must be comprehensively proven with site references
531 |  |  | 5 | [5 empty] | Comprehensive walkthroughs of the module
532 |  |  | 6 | [5 empty] | In-depth consultation with Client subject matter experts
533 |  |  | 7 | [5 empty] | Develop best practice standards for configuration
534 |  |  | 8 | [5 empty] | Develop Client module specific codes facilitated by JAR
535 |  |  | 9 | [5 empty] | Coordinated with Estimating and Contract Costing
536 |  |  | 10 | [5 empty] | Laboratory configuration and testing
537 |  |  |  | 1 | [5 empty] | Develop workflows, standards, policies and protocols
538 |  |  |  | 2 | [5 empty] | Develop comprehensive statistically representative data and situation test pack
539 |  |  |  | 3 | [5 empty] | Configure in the Laboratory, test and refine
540 |  |  |  | 4 | [5 empty] | Specify, document and test module processes
541 |  |  |  | 5 | [5 empty] | Specify and develop module specific Computer Based Training material
542 |  |  |  | 6 | [5 empty] | Final presentation and walkthrough of entire solution with executives
543 |  |  | 11 | [5 empty] | Other Payroll module related configuration and integration activities
544
545
546 | [7 empty] | Total Payroll
547
548
549 | [6 empty] | Total Finance and Administration
550
551
552 | 8 | [5 empty] | Integrated Laboratory testing and laboratory simulation operation
553 |  | 1 | [5 empty] | Establishment of Laboratory
554 |  |  | 1 | [5 empty] | Detailed planning of integrated laboratory simulation programme
555 | [9 empty] | -- goal of the laboratory is to BREAK IT until IT cannot be broken
556 |  |  | 2 | [5 empty] | Specify laboratory facility
557 |  |  | 3 | [5 empty] | Procure equipment and establish laboratory facility
558 |  |  | 4 | [5 empty] | Collate and consolidate detailed statistically significant test packs for each module into one integrated test pack
559
560
561 | [7 empty] | Total Establishment of Laboratory
562
563 |  | 2 | [5 empty] | Testing of individual modules
564 |  |  | 1 | [5 empty] | Commission and test individual modules in the laboratory as they become available -- see list above
565
566
567 | [8 empty] | Total Testing of invidiual modules -- details listed on a per module basis in preceding sections NOT included here
568
569 |  | 3 | [5 empty] | Test Integration
570 |  |  | 1 | [5 empty] | Test integration of modules as they become available
571
572
573 | [8 empty] | Total Testing of integration as modules become available
574
575 |  |  | 2 | [5 empty] | Testing and acceptance of the integrated solution
576 |  |  |  | 1 | [5 empty] | Technical integration
577 |  |  |  |  | 1 | [5 empty] | Technical testing of integrated solution until the entire solution works technically -- 3 iterations
578 |  |  |  |  | 2 | [5 empty] | Other activities necessary to get the integrated solution to a point where it can be utilized by the business team -- 3 iterations
579
580 |  |  |  | 2 | [5 empty] | Business operational integration
581 |  |  |  |  | 1 | [5 empty] | Operational testing of the integrated solution until the entire solution works at a business operational level -- 3 iterations
582 |  |  |  |  | 2 | [5 empty] | Other activities necessary to get the integrated solution to a point where it can be presented to executives -- 3 iterations
583
584 |  |  |  | 3 | [5 empty] | Simulation and review of integrated solution -- first iteration
585 |  |  |  |  | 1 | [5 empty] | Comprehensive simulation of live operation with small but statistically significant test data pack
586 |  |  |  |  | 2 | [5 empty] | Systematic presentation and walkthrough of entire solution with executives
587 |  |  |  |  | 3 | [5 empty] | Other activities relative to first iteration
588
589 |  |  |  | 4 | [5 empty] | Simulation and review of integrated solution -- second iteration
590 |  |  |  |  | 1 | [5 empty] | Revise, refine and optimise solution
591 |  |  |  |  | 2 | [5 empty] | Comprehensive simulation of live operation with small but statistically significant test data pack until ready to present to execs
592 |  |  |  |  | 3 | [5 empty] | Systematic presentation and walkthrough of entire solution with executives
593 |  |  |  |  | 4 | [5 empty] | Other activities relative to second iteration
594
595 |  |  |  | 5 | [5 empty] | Simulation and review of integrated solution -- third iteration
596 |  |  |  |  | 1 | [5 empty] | Revise, refine and optimise solution
597 |  |  |  |  | 2 | [5 empty] | Comprehensive simulation of live operation with small but statistically significant test data pack until ready to present to execs
598 |  |  |  |  | 3 | [5 empty] | Systematic presentation and walkthrough of entire solution with executives
599 |  |  |  |  | 4 | [5 empty] | Other activities relative to third iteration
600
601
602 | [8 empty] | Total Testing of Integrated Solution
603
604 |  | 4 | [5 empty] | Development and testing of integrated reports and BI models, etc
605 |  |  | 1 | [5 empty] | Development of integrated reports -- 3 iterations with Executive review
606 |  |  | 2 | [5 empty] | Development of integrated BI reports, models and dashboards -- 3 iterations with executive review
607 |  |  | 3 | [5 empty] | Development of executive level strategic BI reports, models and dashboards -- 3 iterations with executive review
608
609
610 | [7 empty] | Total development and testing of integrated reports and BI models, etc
611
612 |  | 5 | [5 empty] | Specification, configuration, testing, refinement and documentation of integrated workflows and operating procedures
613 |  |  | 1 | [5 empty] | Specify and configure workflows and operating procedures -- iteration 1
614 |  |  |  | 1 | [5 empty] | Define workflows from executive level and document
615 |  |  |  | 2 | [5 empty] | Review and refine with management
616 |  |  |  | 3 | [5 empty] | Review and refine with operational personnel
617 |  |  |  | 4 | [5 empty] | Configure in the system
618 |  |  |  | 5 | [5 empty] | Walkthrough
619
620 |  |  | 2 | [5 empty] | Specify and configure workflows and operating procedures -- iteration 2
621 |  |  |  | 1 | [5 empty] | Define workflows from executive level and document
622 |  |  |  | 2 | [5 empty] | Review and refine with management
623 |  |  |  | 3 | [5 empty] | Review and refine with operational personnel
624 |  |  |  | 4 | [5 empty] | Configure in the system
625 |  |  |  | 5 | [5 empty] | Walkthrough
626
627 |  |  | 3 | [5 empty] | Specify and configure workflows and operating procedures -- iteration 3
628 |  |  |  | 1 | [5 empty] | Define workflows from executive level and document
629 |  |  |  | 2 | [5 empty] | Review and refine with management
630 |  |  |  | 3 | [5 empty] | Review and refine with operational personnel
631 |  |  |  | 4 | [5 empty] | Configure in the system
632 |  |  |  | 5 | [5 empty] | Walkthrough
633
634 |  |  | 4 | [5 empty] | Finalize and accept workflows
635 |  |  |  | 1 | [5 empty] | Management review
636 |  |  |  | 2 | [5 empty] | Executive review
637 |  |  |  | 3 | [5 empty] | Acceptance
638
639
640 | [7 empty] | Total specification, configuration, testing, refinement and documentation of integrated workflows
641
642 |  | 6 | [5 empty] | Development of training materials
643 |  |  | 1 | [5 empty] | Documentation of policies and standards -- 3 iterations
644 |  |  | 2 | [5 empty] | Development of user manuals -- 3 iterations
645 |  |  | 3 | [5 empty] | Development of Computer Based Training material with tests and performance measures with executive review -- 3 itns
646 |  |  | 4 | [5 empty] | Other activities necessary to develop a comprehensive training environment for the enterprise
647
648
649 | [7 empty] | Total development of training materials
650
651 |  | 7 | [5 empty] | Training
652 |  |  | 1 | [5 empty] | Training of Operational Personnel
653 |  |  |  | 1 | [5 empty] | Overall system operation, integration impacts -- who is affected by what I do -- how the whole system fits together
654 |  |  |  | 2 | [5 empty] | Policies, standards, protocols, escalation, authories, etc
655 | [10 empty] | -- includes speed and accuracy of data capture for all personnel with significant keyboard input requirements
656 |  |  |  | 3 | [5 empty] | Touch typing test for all personnel responsible for significant keyboard input
657 | [10 empty] | -- touch typing classes for those who do not achieve a minimum standard of 20 words per minute at 99% accuracy
658 | [10 empty] | -- team must include an instructor
659 |  |  |  | 4 | [5 empty] | Training on CBT until reach required standard -- multiple repetitive cycles
660 |  |  |  | 5 | [5 empty] | Comprehensive operational simulation until all staff trained to level where they can migrate to new system easily --at least 3 itns
661 |  |  |  | 6 | [5 empty] | Other training related activities for operational personnel
662 |  |  |  | 7 | [5 empty] | Declaration of operational readiness
663
664
665 | [8 empty] | Total Training of Operational Personnel
666
667 |  |  | 2 | [5 empty] | Training of Supervisory Personnel
668 |  |  |  | 1 | [5 empty] | Overall system operation, integration impacts -- who is affected by what I do -- how the whole system fits together
669 |  |  |  | 2 | [5 empty] | Policies, standards, protocols, escalation, authoriies, etc
670 | [10 empty] | -- includes speed and accuracy of data capture for all personnel with significant keyboard input requirements where applicable
671 |  |  |  | 3 | [5 empty] | Touch typing test for all personnel responsible for significant keyboard input
672 | [10 empty] | -- touch typing classes for those who do not achieve a minimum standard of 20 words per minute at 99% accuracy
673 |  |  |  | 4 | [5 empty] | Training on CBT until reach required standard where applicable -- multiple repetitive cycles
674 |  |  |  | 5 | [5 empty] | Comprehensive training in conjunction with operational simulation until all supervisory staff are trained to a level where they
675 | [10 empty] | can migrate to the new system easily -- at least 3 iterations
676 |  |  |  | 6 | [5 empty] | Other training related activities for supervisory personnel
677 |  |  |  | 7 | [5 empty] | Declaration of supervisory readiness
678
679
680 | [8 empty] | Total Training of Supervisory Personnel
681
682 |  |  | 3 | [5 empty] | Training of Managers
683 |  |  |  | 1 | [5 empty] | Overall system operation, integration impacts -- who is affected by what I do -- how the whole system fits together
684 |  |  |  | 2 | [5 empty] | Policies, standards, protocols, escalation, authoriies, etc
685 | [10 empty] | -- includes speed and accuracy of data capture for all personnel with significant keyboard input requirements where applicable
686 |  |  |  | 3 | [5 empty] | Touch typing test for all personnel responsible for significant keyboard input
687 | [10 empty] | -- touch typing classes for those who do not achieve a minimum standard of 20 words per minute at 99% accuracy
688 |  |  |  | 4 | [5 empty] | Comprehensive training in conjunction with operational simulation until all managers are trained to a level where they
689 | [10 empty] | can migrate to the new system easily -- at least 3 iterations
690 |  |  |  | 5 | [5 empty] | Other training related activities for managers
691 |  |  |  | 6 | [5 empty] | Declaration of management readiness
692
693
694 | [8 empty] | Total Training of Managers
695
696 | [7 empty] | Total Training
697
698 |  | 8 | [5 empty] | Formal declaration of readiness to commence live operation -- issue certificate of readiness
699 |  |  | 1 | [5 empty] | Declaration by implementer Team Leader
700 |  |  | 2 | [5 empty] | Declaration by implementer Project Manager
701 |  |  | 3 | [5 empty] | Declaration by implementer Project Director
702 |  |  | 4 | [5 empty] | Declarations by Client Heads of Departments
703 |  |  | 5 | [5 empty] | Declaration by Client Project Facilitator
704 |  |  | 6 | [5 empty] | Declaration by Client Contract Manager
705 |  |  | 7 | [5 empty] | Declaration by Client Executive Sponsor
706 |  |  | 8 | [5 empty] | Approval by EXCO
707 |  |  | 9 | [5 empty] | Board approval
708 |  |  | 10 | [5 empty] | Partial Release of Retention
709
710
711 | [7 empty] | Total declaration of readiness to commence live operation
712
713 | [6 empty] | Total Integrated Laboratory testing and laboratory simulation operation
714
715
716 | 9 | [5 empty] | Custom Development -- lump sum budget provision -- all stages 3 iterations with Executive review
717 | [8 empty] | -- Custom development ONLY undertaken in extreme circumstances where it is essential to support core strategic differentiators
718 | [8 empty] | -- It is expected that Precision Configuration that accurately models the real world will minimize the need for custom development
719 |  | 1 | [5 empty] | Propose possible custom development
720 |  | 2 | [5 empty] | Concept specification
721 |  | 3 | [5 empty] | Develop business case
722 |  | 4 | [5 empty] | Review and refine business case
723 |  | 5 | [5 empty] | Formal approval
724 |  | 6 | [5 empty] | Detailed specification
725 |  | 7 | [5 empty] | Development
726 |  | 8 | [5 empty] | Testing
727 |  | 9 | [5 empty] | Acceptance
728 |  | 10 | [5 empty] | Deployment in the Laboratory
729 |  | 11 | [5 empty] | Comprehensive integrated testing -- break it until it cannot be broken -- 3 iterations
730 |  | 12 | [5 empty] | Other custom development activities
731
732
733 | [6 empty] | Total Custom Development -- lump sum provision
734
735
736 | 10 | [5 empty] | Overall System Integration
737 | [8 empty] | -- Impacts all systems, modules and components
738 |  | 1 | [5 empty] | Develop comprehensive integration schema
739 |  | 2 | [5 empty] | Develop coding standards for integration
740 |  | 3 | [5 empty] | Develop operational "way of working" standards for integration
741 |  | 4 | [5 empty] | Develop test packs for integration
742 |  | 5 | [5 empty] | Oversee all aspects of integration testing in the Laboratory
743 |  | 6 | [5 empty] | Certify that integration is fully tested and ready for deployment
744 |  | 7 | [5 empty] | Other integration activities
745
746
747 | [6 empty] | Total Overall System Integration
748
749
750 | 11 | [5 empty] | General System Requirements
751 | [8 empty] | -- Impacts all systems, modules and components
752 |  | 1 | [5 empty] | Multi-company and multi-currency operation
753 |  | 2 | [5 empty] | Remote connectivity or batch synchronization for isolated areas
754 |  | 3 | [5 empty] | Simulate cross-border operation including interfacing with third party systems such as customs and clearing
755 |  | 4 | [5 empty] | Simulate operation in remote areas
756 |  | 5 | [5 empty] | Other general system functionality and capability activities
757
758
759 | [6 empty] | Total General System Requirements
760
761
762 | 12 | [5 empty] | Operational commissioning and ramp-up to formal handover including fine tuning and bedding down
763 |  | 1 | [5 empty] | Develop detailed commissioning plan at the level of each business unit and each functional area -- exec review -- 3 itns
764
765
766 | [7 empty] | Total planning for operational commissioning
767
768 |  | 2 | [5 empty] | Commissioning in xxx2
769 |  |  | 1 | [5 empty] | Pre-commissioning communication and change facilitation per area commissioned
770 | [9 empty] | -- what we are going to do -- what we are doing -- what we have done
771 | [9 empty] | -- note that "support" includes hot-line support
772 |  |  | 2 | [5 empty] | Support for one week prior to commissioning
773 |  |  | 3 | [5 empty] | Support over the 48 hours covering commissioning
774 |  |  | 4 | [5 empty] | Support for next five business days
775 |  |  | 5 | [5 empty] | Support for the next 15 business days
776 |  |  | 6 | [5 empty] | Additional support over first month end
777 |  |  | 7 | [5 empty] | Support for the next fiscal month
778 |  |  | 8 | [5 empty] | Support for the next three fiscal months
779 |  |  | 9 | [5 empty] | Support for the next six fiscal months
780 |  |  | 10 | [5 empty] | Additional support over first year end
781 |  |  | 11 | [5 empty] | Additional support for first three months after year end
782 |  |  | 12 | [5 empty] | Other support
783
784
785 | [7 empty] | Total Commissioning in xxx2
786
787 |  | 3 | [5 empty] | Commissioning in xxx1
788 |  |  | 1 | [5 empty] | Pre-commissioning communication and change facilitation per area commissioned
789 | [9 empty] | -- what we are going to do -- what we are doing -- what we have done
790 | [9 empty] | -- note that "support" includes hot-line support
791 |  |  | 2 | [5 empty] | Support for one week prior to commissioning
792 |  |  | 3 | [5 empty] | Support over the 48 hours covering commissioning
793 |  |  | 4 | [5 empty] | Support for next five business days
794 |  |  | 5 | [5 empty] | Support for the next 15 business days
795 |  |  | 6 | [5 empty] | Additional support over first month end
796 |  |  | 7 | [5 empty] | Support for the next fiscal month
797 |  |  | 8 | [5 empty] | Support for the next three fiscal months
798 |  |  | 9 | [5 empty] | Support for the next six fiscal months
799 |  |  | 10 | [5 empty] | Additional support over first year end
800 |  |  | 11 | [5 empty] | Additional support for first three months after year end
801 |  |  | 12 | [5 empty] | Other support
802
803
804 | [7 empty] | Total Commissioning in xxx1
805
806 |  | 4 | [5 empty] | Commissioning at xxx3 -- very limited scope
807 |  |  | 1 | [5 empty] | Pre-commissioning communication and change facilitation per area commissioned
808 | [9 empty] | -- what we are going to do -- what we are doing -- what we have done
809 | [9 empty] | -- note that "support" includes hot-line support
810 |  |  | 2 | [5 empty] | Support for one week prior to commissioning
811 |  |  | 3 | [5 empty] | Support over the 48 hours covering commissioning
812 |  |  | 4 | [5 empty] | Support for next five business days
813 |  |  | 5 | [5 empty] | Support for the next 15 business days
814 |  |  | 6 | [5 empty] | Additional support over first month end
815 |  |  | 7 | [5 empty] | Other support
816
817
818 | [7 empty] | Total Commissioning in xxx3
819
820 |  | 5 | [5 empty] | Formal declaration of project completion and final handover to Client
821 |  |  | 1 | [5 empty] | Declaration by implementer Team Leader
822 |  |  | 2 | [5 empty] | Declaration by implementer Project Manager
823 |  |  | 3 | [5 empty] | Declaration by implementer Project Director
824 |  |  | 4 | [5 empty] | Declarations by Client Heads of Departments
825 |  |  | 5 | [5 empty] | Declaration by Client Project Facilitator
826 |  |  | 6 | [5 empty] | Declaration by Client Contract Manager
827 |  |  | 7 | [5 empty] | Declaration by Client Executive Sponsor
828 |  |  | 8 | [5 empty] | Approval by EXCO
829 |  |  | 9 | [5 empty] | Board approval
830 |  |  | 10 | [5 empty] | System is now in full, stable operation
831 |  |  | 11 | [5 empty] | Formal handover event
832 |  |  | 12 | [5 empty] | Release of Retention
833
834
835 | [7 empty] | Total declaration of project completion and formal handover
836
837 | [6 empty] | Total Operational Commissioning, Ramp-Up and Handover
838
839
840 | 13 | [5 empty] | Operational support per 12 month period from anniversary of handover
841 |  | 1 | [5 empty] | Ongoing support
842 |  | 2 | [5 empty] | System elaboration
843 |  | 3 | [5 empty] | Upgrades
844 |  | 4 | [5 empty] | Other operational support
845
846 | [6 empty] | Total Operational support first year of full operation
847
848
849 | 14 | [5 empty] | Contingency
850 |  | 1 | [5 empty] | Implementer discretion contingency if required by bidder
851 |  | 2 | [5 empty] | Client discretion contingency only released with Client approval
852
Grand Totals
Cross Cast -- Error Check
I the undersigned …………………………………….. (name) hereby certify that this schedule has been rigorously quality controlled and represents the definitive pricing for Professional Services for the Client Business System and ERP Project and confirm that …………………………………… (name of company) will deliver the required solution for the prices shown here on a fixed price per component basis with a tolerance of 10%, that is that the final offer price will not be more than 10% greater than the price above -- for Stage 1 of the bid process